## Assumptions
INNOVA — BOTTOM-UP SCOPE, EFFORT & BUDGET MODEL
Konekti INTERNAL · Full scope (5 work packages) · Effort priced at day-rate; calendar modelled separately. Rev 4 — self-hosted Airbyte connectors, license €7,500/mo confirmed.
1 · PRICING & EFFORT DRIVERS (blue = inputs you change)
Blended day rate (€/day) | 1100 | Adam's stated average across roles. Used to price ALL effort.
Working days per week | 5 | For converting weeks <-> days.
Day-rate sensitivity — low | 1000 | Lower price bound.
Day-rate sensitivity — high | 1250 | Upper price bound.
2 · CONTINGENCY ON EFFORT (layered — applied to man-days, not calendar)
Base contingency (all packages) | 15% | Standard estimation buffer on every WP. Covers normal underestimation.
Risk uplift — high-uncertainty WPs | 25% | EXTRA, applied only to flagged WPs (WP3 attribution/identity, WP4 finance source, custom CDK builds).
Client-responsiveness rework premium | 8% | Effort added by context-switching/cold-restart IF client is slow. 0% if highly responsive.
3 · CALENDAR DRIVERS (separate from cost — drive elapsed time only)
Konekti delivery capacity (people on it) | 1.5 | Avg FTE actively delivering (analyst + dev capacity blended). Drives how fast effort burns down.
Flow efficiency — fast/responsive client | 65% | % of calendar that is productive work. High = compressed timeline (CEO 'fast ~6mo').
Flow efficiency — realistic | 50% | Normal back-and-forth (CEO 'realistic ~9mo').
Flow efficiency — slow/unresponsive client | 35% | Waiting on access, answers, approvals (CEO 'up to ~12mo').
4 · COMMERCIAL (recurring)
Konekti license €/month (5 seats) | 7500 | CONFIRMED monthly. Annualised on Scenarios tab.
License months in year 1 | 12 | Set lower if licence starts mid-project.
KEY MODELLING NOTES
• EFFORT vs CALENDAR are decoupled. Effort (man-days) sets COST and never changes with client speed (except the small rework premium). CALENDAR (elapsed months) is a separate output driven by capacity + flow efficiency — this is the 6/9/12-month spread.
• Connectors are SELF-HOSTED Airbyte + custom CDK builds. No monthly connector subscription. The work is one-off BUILD EFFORT, already inside WP effort. Only ongoing recurring cost is the Konekti license + LLM usage.
• LLM API usage (OpenAI/Anthropic/Gemini, client-cloud-hosted) is a pass-through, still being defined. NOT in totals.

## Effort Build-Up
EFFORT BUILD-UP — man-days by work package (the cost foundation)
Spine = CTO-agreed connector time (4 wks build + 2 wks setup, self-hosted Airbyte) + Adam's modelling/analytics weeks, decomposed across the 5 WPs. 'High-risk?' flags which WPs get the extra risk uplift.
Work package / activity | Layer | Dev days | Analyst days | Base days | High-risk? | Risk days | Cost (base+cont.) | Notes
Redshift warehouse + dbt foundation | 1 | 10 | 0 | 10 | — | 0 | 12650 | CTO-agreed: 2 wks. Raw/staging/mart, dbt init, self-hosted Airbyte infra stood up.
Connector builds — existing Airbyte sources | 1 | 10 | 0 | 10 | — | 0 | 12650 | ~half the 10 sources exist in Airbyte; fast config. Part of CTO 4-wk connector estimate.
Connector builds — custom CDK sources | 1 | 10 | 0 | 10 | Yes | 2.5 | 15400 | Custom CDK for sources not in Airbyte (e.g. Eloqua activity, Dynamics audit, internal dashboard). Higher uncertainty.
WP1 — Channel efficiency (CPL, CPA) | 2-3 | 3 | 6 | 9 | — | 0 | 11385 | Ad platforms + GA4 + Search Console + CRM lead counts. Cost per lead / per action by channel. FASTEST metric to value. (CPS needs deal join -> WP2.)
WP2 — Acquisition economics (CPS, CAC by source) | 2-3 | 2 | 6 | 8 | — | 0 | 10120 | Adds CRM pipeline + lead-source + closed-deal join. Cost per SALE and CAC by source. 'Sale' = closed deal/subscription in Dynamics, not an ad event.
WP3 — Click-to-revenue attribution | 2-3 | 12 | 8 | 20 | Yes | 5 | 30800 | Identity stitching click->lead->deal. 'Which channel drives REVENUE.' First/last/data-driven models. The hard one.
WP4 — Unit economics (LTV, LTV:CAC) | 2-3 | 4 | 5 | 9 | Yes | 2.25 | 13860 | Adds finance/orders realised revenue, joined to accounts. Real LTV and LTV:CAC by source.
Analytics & AI — modelling that fuels reports | 3 | 0 | 8 | 8 | — | 0 | 10120 | ANALYST side: anomaly logic, forecast models, the analytics behind alerts/reports, NL Q&A model in Konekti.
Automation & downstream wiring (Konekti + n8n + Teams) | 3 | 15 | 0 | 15 | — | 0 | 18975 | DEV side: wire Konekti outputs into n8n workflows, push automated reports to Teams, build alert plumbing & integrations. Min. 15 days; runs in parallel across the project.
Handover: docs, training, SLA | 4 | 2 | 5 | 7 | — | 0 | 8855 | Lightweight.
TOTAL — base effort |  | 68 | 38 | 106 |  | 9.75 | 144815
Loaded effort incl. contingency (days) |  |  |  | 131.65 |  |  | 144815 | Excl. client-responsiveness rework premium (added in Scenarios).

## Scenarios
SCENARIOS — cost (effort) and calendar (time) shown SEPARATELY
A · COST — driven by EFFORT (changes little with client speed)
Scenario | Effort (days) | Rework premium | Total cost (services) | Driver
Responsive client | 131.65 | 0 | 144815 | No restarts; rework premium not applied
Realistic | 136.916 | 5792.6 | 150607.6 | Half the rework premium — normal friction
Slow client | 142.182 | 11585.2 | 156400.2 | Full rework premium — cold restarts add effort
B · CALENDAR — driven by client RESPONSIVENESS (does NOT change the price)
Scenario | Effort (days) | Flow efficiency | Elapsed months | CEO's read
Fast / responsive | 131.65 | 65% | 6.2224 | ~6 months ('fast' per CEO)
Realistic | 136.916 | 50% | 8.4127 | ~9 months ('realistic' per CEO)
Slow / unresponsive | 142.182 | 35% | 12.4803 | up to ~12 months per CEO
C · YEAR-ONE ALL-IN (services + first-year Konekti license)
Scenario | Services | License (yr 1) | Year-1 total | Note
Low (responsive) | 144815 | 90000 | 234815 | Floor; clean & fast
Realistic | 150607.6 | 90000 | 240607.6 | Plan around this
High (slow + risk realised) | 156400.2 | 90000 | 246400.2 | Slow client; risk WPs overrun
+ LLM API usage: TBD pass-through, NOT included. + Year-2 onward: license €90k/yr recurring.
HOW TO USE THIS: the COST (block A) is what you quote and what it costs you to deliver — it barely moves with client speed. The CALENDAR (block B) is the timeline COMMITMENT — that's what flexes 6->9->12 months on client responsiveness. Quote a fixed price band off block A; commit to a timeline RANGE off block B, with a clause that elapsed time assumes agreed client response SLAs (access, answers, approvals).

## WP1 First Quote
WP1 — FIRST-QUOTE PACKAGE (lead with this)
Quote ONE package tight first. WP1 = Channel efficiency: CPL / CPA by channel — the fastest of Andrzej's named metrics to deliver. NOTE: this assumes the FULL foundation is built first — full Redshift config, ALL connectors, then dbt on top — because the data model and later WPs all depend on it. So WP1's price carries the whole foundation.
Component | Days | Cost | Note
Full Redshift configuration | 10 | 11000 | Complete warehouse setup: raw/staging/mart scaffolding.
All connectors built (existing Airbyte + custom CDK) | 30 | 33000 | Every source landed — existing config + custom CDK builds. The full Layer-1 effort up front.
dbt + transformation layer on landed data | 10 | 11000 | Built once all connectors are landing; the modelling backbone.
Model channel efficiency (CPL/CPA) + NL Q&A | 6 | 6600 | Analyst side: the WP1 metric model + conversational layer.
Lightweight handover for WP1 | 3 | 3300 | Docs + walkthrough for first package.
WP1 base | 59 | 64900
WP1 with 15% contingency | 67.85 | 74635 | The narrow first-quote number.
Sequence the rest (WP2->WP4 + analytics layer) after WP1 lands and the tech answers tighten the risk WPs.

## WP Map (metrics)
WORK PACKAGES ANCHORED TO ANDRZEJ'S METRICS
Each WP = a metric Andrzej named + the question it answers + the data it needs. Ordered fastest-metric-to-value. End-to-end view is built iteratively: every WP adds the next layer of the click->lead->deal->revenue funnel.
Work package | Metric(s) answered | Andrzej's question | Data needed | Order
Foundation | (enabling) | Stand up the warehouse so anything can land | Redshift + dbt + self-hosted Airbyte | 0 — first
WP1 Channel efficiency | CPL, CPA | What does each channel cost per lead / per action? | Ad platforms, GA4, Search Console, CRM lead counts | 1 — fastest value
WP2 Acquisition economics | CPS, CAC by source | Cost per SALE, and which sources produce DEALS not just leads? | + CRM pipeline, lead-source & closed-deal join | 2
WP3 Click-to-revenue attribution | Channel->revenue; first/last/data-driven | Which channel actually drives REVENUE? Under which attribution model? | + identity stitching click->lead->deal (UTM/click-ID) | 3 — hardest
WP4 Unit economics | LTV, LTV:CAC | What is real LTV and LTV:CAC per source? | + finance/orders realised revenue, joined to accounts | 4 — deepest data
Analytics & AI layer | All, conversational | Alerts, weekly Teams reports, forecasting, ask-in-plain-language | Full model (cross-cutting) | Throughout
Automation & downstream wiring | (delivery) | Push reports to Teams, n8n workflows, alert plumbing | Konekti + n8n + Teams integration (dev) | Throughout
WHY THIS ORDER: the metrics have a natural dependency chain that also matches data-source readiness. CPL/CPA need only spend + lead counts (fast). CAC adds won-deal linkage. Channel->revenue needs identity resolution (hard). LTV:CAC needs realised revenue (deepest). So sequencing by fastest-metric-to-value ALSO builds the end-to-end funnel in the only order the data allows — no conflict between 'quick wins' and 'full picture'.

## Parallel Workflow
PARALLEL DELIVERY — dev lands a source, Konekti models it, dev flips to next
The handoff: source connected -> landed structure in Redshift (dev) -> objects/activities modelled in Konekti (Adam) -> insights/reports/automations out. As soon as one source lands, Adam models while dev moves to the next. Calendar shown realistic (~9mo); compresses with a responsive client.
Stream | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9
Foundation (Redshift/dbt/Airbyte)
DEV: land WP1 sources
ANALYST: model WP1 (CPL/CPA)
DEV: land WP2 sources
ANALYST: model WP2 (CPS/CAC)
DEV: land WP3 sources + identity
ANALYST: model WP3 (attribution)
DEV: land WP4 finance source
ANALYST: model WP4 (LTV:CAC)
Analytics/AI: alerts, Teams, forecast, Q&A
Handover, docs, training, SLA
Legend: | Dev | Analyst | Analytics
First usable metric (WP1 CPL/CPA) lands ~M2-M3, not at the end. Each later WP delivers its metric as its data lands, so Andrzej sees value continuously while the end-to-end model fills in.